## Slide 2: SPCA QC Story

## Slide 3: Problem Statement:
Unable to start the assigned task as per calendar.
Giving priority to another assignment which was not in calendar initially.
Not informing the PM on the delay until EOD.
Notes: 3

## Slide 4: Details of the Problem Statement:
  Lance booked my calendar from 18/04/2023 to 20/04/2023 for SPCA pen test fixes.
  Without checking my assignments in calendar, I have committed to Helen for UAT fixes of another ongoing project (Cubeforall). Take note, the calendar was not booked for this project until then.
  Due to Cubeforall fixes, SPCA got delayed. I only informed Lance not immediately, but in EOD, which created more challenge for Lance to manage his client.

## Slide 5: Actions Taken to resolve:
  The issue was escalated to Glenn (Team Leader) by WMP team, and he took immediate actions to fire-fight the situation.
  We listed down all the assignments in hand, together with the committed due dates. Based on the same, Glenn has helped to plan out my priorities and assignments to handle during the weekend (No OT was allowed) to cover up the delays. Some projects were passed down to Bhupesh temporarily to divide the work load.
  All such PLAN B was proposed by Glenn, gotten approval from others PMs, and then execute accordingly.

## Slide 6: Steps to Avoid this Problem in the future:
We need to check our assignments first in Calendar before committing to any timeline to any PMs.
Need to check if any assigned task is not added to Calendar. If yes, inform the respective PM or add the task in Calendar myself.
Managing my timeline well, and inform the PM much before-hand for any possible delays, so that it is less troublesome for the PM to handle his client’s expectations.
Inform my TL immediately if there is a lot of assigned urgent tasks in one single day, so that he can plan for me and help to avoid such situations.

## Slide 7: Lessons Learnt
We need to check our assignments first in Calendar before committing to any timeline to any PMs.
Need to check if any assigned task is not added to Calendar. If yes, inform the respective PM or add the task in Calendar myself.
Managing my timeline well, and inform the PM much before-hand for any possible delays, so that it is less troublesome for the PM to handle his client’s expectations.
Inform my TL immediately if there is a lot of assigned urgent tasks in one single day, so that he can plan for me and help to avoid such situations.

## Slide 8: Thank You